## Slide 1
---
marp: true
theme: engineering
paginate: true
math: katex
header: 'Session 15: Technical Management & Enabling Processes'

## Slide 2: Technical Management & Enabling Processes
Session 15 | Automotive Vehicles (AEL ZC441)

## Slide 3: Title
Welcome to Session 15: Technical Management and Enabling Processes. Today we explore the often-overlooked half of systems engineering.
We've spent most of this course on TECHNICAL processes: requirements, architecture, verification. But successful SE requires MANAGEMENT processes and ENABLING processes.
Without these, even perfect technical processes fail.
PPT Content:
SESSION 15: TECHNICAL MANAGEMENT & ENABLING PROCESSES The Management Foundation for Technical Excellence Module 4: Lifecycle & Trends Automotive Systems Engineering (AE ZG517 / AEL ZG517)
Outcomes Addressed: Setting context for LO3, LO5

## Slide 4: Connection to Previous Sessions
Let's see how we got here:
Sessions 1-8 (Technical Processes): — Requirements, architecture, verification, validation
The 'WHAT' and 'HOW' of systems engineering
Sessions 9-12 (Project Management & Specialty): — Project management, risk, quality, safety & security
Managing technical execution
Session 13 (Lifecycle Cost): — Economic perspective on SE decisions
Total cost of ownership
Session 14 (Case Study 2): — Applied SE analysis to real-world failure
Session 15 (Today): Technical Management & Enabling Processes — The processes that make technical processes work
Knowledge, measurement, decision-making
Planning, control, portfolio management
This completes the ISO/IEC 15288 process framework.
PPT Content:
THE SYSTEMS ENGINEERING JOURNEY Sessions 1-8: Technical Processes Foundation • Requirements, architecture, design • Integration, verification, validation Sessions 9-12: Project Management & Specialty • Project, risk, quality management • Safety & security engineering Sessions 13-14: Lifecycle & Application • LCC & TCO • Real-world case analysis Session 15: Management & Enabling ← TODAY • Technical management processes • Enabling organizational processes Session 16: Emerging Trends (Next)

## Slide 5: The Three Process Categories - ISO/IEC 15288
ISO/IEC 15288 organizes SE processes into THREE categories:
TECHNICAL PROCESSES (8 processes): — Business/Mission Analysis
Stakeholder Needs & Requirements
System Requirements
Architecture Definition
Design Definition
System Analysis
Implementation
Integration, Verification, Validation
We've covered these extensively in Sessions 1-14.
TECHNICAL MANAGEMENT PROCESSES (8 processes): — Project Planning
Project Assessment & Control
Decision Management
Risk Management
Configuration Management
Information Management
Measurement
Quality Assurance
We've touched on some (Sessions 9-12), today we dive deeper.
ORGANIZATIONAL PROJECT-ENABLING PROCESSES (5 processes): — Life Cycle Model Management
Infrastructure Management
Portfolio Management
Human Resource Management
Quality Management
These enable all other processes. Often neglected, but critical.
Today we focus on the management and enabling processes that make technical excellence possible.
PPT Content:
ISO/IEC 15288: THREE PROCESS CATEGORIES TECHNICAL PROCESSES (8) • Requirements, architecture, design • Implementation, verification, validation → Sessions 1-14 coverage TECHNICAL MANAGEMENT PROCESSES (8) • Project planning & control • Decision, risk, configuration mgmt • Measurement, quality assurance → Today's focus (Part 1) ORGANIZATIONAL ENABLING PROCESSES (5) • Lifecycle model, infrastructure, portfolio • Human resources, quality management → Today's focus (Part 2) **All three categories required for SE success**

## Slide 6: Why Management Processes Matter - Real Costs
Let me show you why today's processes are critical:
Industry data on project failures: — 68% of software-intensive projects fail due to poor requirements management (Standish Group)
75% of large automotive projects exceed budget/schedule (McKinsey)
#1 cause: Inadequate technical planning and control
#2 cause: Poor decision-making processes
#3 cause: Lack of knowledge management
Automotive examples: — Boeing 737 MAX: Poor configuration management led to MCAS version confusion
VW Dieselgate: Inadequate quality assurance and measurement
Tesla Autopilot delays: Knowledge management gaps between teams
The paradox: Technical processes get attention, but management processes prevent failures.
Today we learn the processes that prevent these failures.
PPT Content:
WHY TECHNICAL MANAGEMENT MATTERS: PROJECT FAILURES Industry Statistics: • 68% of projects fail due to poor requirements mgmt • 75% of automotive projects exceed budget/schedule • Top causes: Planning, decision-making, knowledge gaps Automotive Failures (Management Gaps): • Boeing 737 MAX: Configuration management • VW Dieselgate: Quality assurance • Tesla delays: Knowledge management **Perfect technical processes ≠ Success** **Need management & enabling processes**

## Slide 7: The Management Gap - What's Missing?
Let me illustrate the management gap with a real scenario:
Project: Next-generation ADAS system
Technical execution: Excellent
Perfect requirements (Session 4 methods applied)
Solid architecture (Session 5 principles used)
Comprehensive V&V (Session 8 coverage achieved)
Project result: Failure
Delivered 18 months late
200% over budget
Customer rejected final system
What went wrong? Not technical processes. Management processes:
Missing Process 1: Technical Planning — No work breakdown structure
No resource allocation
No schedule integration
Missing Process 2: Decision Management — Architecture decisions revisited 5 times
No decision framework
Stakeholder conflicts unresolved
Missing Process 3: Measurement — No progress tracking
No quality metrics
Problems discovered too late
Missing Process 4: Knowledge Management — Lessons from previous projects not captured
Expert knowledge siloed
New team members reinventing solutions
This is why we need today's session. Management processes are the foundation.
PPT Content:
THE MANAGEMENT GAP: WHY GOOD TECH FAILS Scenario: Next-gen ADAS Project Technical Execution: ✓ Excellent • Perfect requirements • Solid architecture • Comprehensive V&V Project Result: ✗ Failure • 18 months late • 200% over budget • Customer rejection Root Causes (Management Gaps): 1. No technical planning → resource chaos 2. No decision framework → rework cycles 3. No measurement → late problem detection 4. No knowledge mgmt → repeated mistakes **Management processes prevent this**

## Slide 8: The Perfect System That Failed
Let me tell you about a real automotive project I'll call 'Advanced Driver Assist Platform' (ADAP):
Technical credentials: Impeccable
Requirements: 2,000+ system requirements, full traceability
Architecture: Modular, scalable, safety-certified ASIL-D
V&V: 95% code coverage, 100% requirement coverage
Team: World-class engineers from top OEMs
Project timeline:
Month 0: Project kickoff, 24-month plan
Month 6: First architecture review - team decides to change sensor suite
Month 8: Architecture decision reversed, return to original
Month 12: Mid-project - no working integration yet
Month 18: Schedule slips to 36 months, budget increased 50%
Month 24: Integration issues discovered (should have been month 12)
Month 30: Customer loses confidence, considers canceling
Month 36: System finally delivered, 12 months late, 80% over budget
Post-mortem findings: — Technical quality: Excellent
Project management: Catastrophic failure
What went wrong? Let's analyze the management process failures.
PPT Content:
CASE: ADVANCED DRIVER ASSIST PLATFORM (ADAP) Technical Excellence: ✓ 2,000+ requirements, full traceability ✓ ASIL-D certified architecture ✓ 95% code coverage, 100% req coverage ✓ World-class engineering team Project Execution: ✗ 12 months late (24 → 36 months) ✗ 80% over budget ✗ Customer nearly canceled ✗ Integration chaos Post-Mortem: Technical quality excellent, management failed **Question: How does this happen?**

## Slide 9: Root Cause Analysis - Management Process Failures
Root cause analysis of ADAP failure revealed SIX management process gaps:
Gap 1: No Decision Management Process — Architecture changes made ad-hoc
No decision criteria framework
Decisions reversed multiple times
Impact: 4 months of rework, $2M wasted
Gap 2: Inadequate Technical Planning — No detailed WBS below subsystem level
No integration milestones defined
Parallel work poorly coordinated
Impact: Late discovery of integration issues
Gap 3: No Measurement System — Progress tracked by 'percent complete' estimates (subjective)
No earned value management
Technical performance not measured
Impact: Problems invisible until month 24
Gap 4: Poor Configuration Management — Multiple architecture versions in use simultaneously
Interface specifications changed without control
Teams worked to different baselines
Impact: Integration failures, incompatible components
Gap 5: Zero Knowledge Management — Previous ADAS project lessons not reviewed
Same integration mistakes repeated
New team members not onboarded with historical context
Impact: Repeated errors, slow learning
Gap 6: No Portfolio Oversight — ADAP competed with 3 other projects for resources
No organizational prioritization
Critical experts pulled to other projects
Impact: Resource thrashing, schedule delays
Key insight: Every gap is a PROCESS gap, not a people gap.
With proper management processes, ADAP would have succeeded on time and budget.
This is what we'll learn today.
PPT Content:
ADAP ROOT CAUSES: MANAGEMENT PROCESS GAPS Gap 1: No Decision Management • Ad-hoc architecture changes • 4 months rework, $2M wasted Gap 2: Inadequate Technical Planning • No integration milestones • Late problem discovery Gap 3: No Measurement System • Subjective progress tracking • Problems invisible until month 24 Gap 4: Poor Configuration Management • Multiple baselines in parallel • Integration failures Gap 5: Zero Knowledge Management • Lessons not captured/applied • Repeated mistakes Gap 6: No Portfolio Oversight • Resource conflicts • Schedule delays **All process gaps, not people gaps** **Fixable with today's processes**

## Slide 10: Technical Planning - Work Breakdown Structure (WBS)
Let's start with Technical Planning. Foundation: Work Breakdown Structure (WBS).
WBS Definition (PMBOK):
'Hierarchical decomposition of total scope of work to accomplish project objectives'
Why WBS matters for SE: — Defines ALL work to be done
Basis for schedule, cost, resource planning
Enables parallel work assignment
Provides control account structure
WBS for Automotive ADAS System:
Level 1: Project — 1.0 ADAS System Development
Level 2: Major Deliverables — 1.1 Requirements Engineering
1.2 System Architecture
1.3 Subsystem Development
1.4 Integration & V&V
1.5 Documentation & Certification
1.6 Project Management
Level 3: Work Packages (Example: 1.3 Subsystem Development) — 1.3.1 Sensor Subsystem (Radar, Camera, Lidar)
1.3.2 Perception Subsystem (Sensor Fusion, Object Tracking)
1.3.3 Decision Subsystem (Path Planning, Behavior Control)
1.3.4 Actuation Subsystem (Steering, Braking Interface)
1.3.5 HMI Subsystem (Display, Alerts)
Level 4: Activities (Example: 1.3.1 Sensor Subsystem) — 1.3.1.1 Radar sensor specification
1.3.1.2 Radar hardware design
1.3.1.3 Radar firmware development
1.3.1.4 Radar unit testing
1.3.1.5 Radar integration
WBS goes to level where: — Work can be assigned to individual/team
Duration can be estimated (±10%)
Cost can be budgeted
Progress can be measured
Typical automotive ADAS WBS: 4-6 levels, 500-2000 work packages
Tools: MS Project, Primavera, JIRA (for agile WBS)
PPT Content:
TECHNICAL PLANNING: WORK BREAKDOWN STRUCTURE (WBS) Definition: Hierarchical decomposition of project scope ADAS System WBS Structure: Level 1: Project (ADAS Development) Level 2: Major Deliverables • Requirements, architecture, subsystems • Integration, V&V, documentation • Project management Level 3: Work Packages • Sensor, perception, decision, actuation, HMI Level 4: Activities • Specification, design, development • Testing, integration WBS Criteria: ✓ Assignable to individual/team ✓ Estimable (±10%) ✓ Budgetable ✓ Measurable **WBS = Foundation for schedule, cost, resources**

## Slide 11: Technical Planning - Schedule Integration
From WBS, we build the Integrated Master Schedule (IMS).
Schedule Integration for ADAS:
Critical path dependencies:
Requirements → Architecture: — Requirements complete (Month 3) → Architecture start
Architecture review gate (Month 6) → Subsystem design start
Parallel Development (Months 6-18): — Sensor subsystem development
Perception subsystem development
Decision subsystem development
All in parallel, different teams
Integration Dependencies (Months 18-24): — Sensor-Perception integration (Month 18)
Perception-Decision integration (Month 20)
System integration (Month 22)
System test (Month 24)
Key scheduling principles:
1. Interface freeze dates: — CAN message definitions frozen Month 8
API specifications frozen Month 10
Prevents late integration chaos
2. Incremental integration: — Not big-bang at Month 22
Continuous integration from Month 18
Hardware-in-Loop (HIL) from Month 12
3. Schedule margin: — 15-20% margin on critical path
Risk mitigation reserve
4. Decision gate alignment: — Gates at Month 6, 12, 18, 24
Go/no-go decisions, not just reviews
Automotive standard practice: — Use critical path method (CPM)
Track with earned value management
Weekly schedule reviews for integration phase
The ADAP failure? No interface freeze, no incremental integration.
PPT Content:
TECHNICAL PLANNING: INTEGRATED MASTER SCHEDULE ADAS Schedule Structure: Phase 1: Requirements & Architecture (Months 0-6) → Gate 1 (Architecture Review) Phase 2: Parallel Subsystem Development (Months 6-18) • Sensor, perception, decision (parallel) → Gate 2 (Design Review) Phase 3: Incremental Integration (Months 18-24) • Sensor-Perception (Month 18) • Perception-Decision (Month 20) • System integration (Month 22) → Gate 3 (System Test Ready) Phase 4: V&V (Months 24-30) → Gate 4 (Production Release) Key Principles: ✓ Interface freeze (Month 8, 10) ✓ Incremental integration (not big-bang) ✓ 15-20% schedule margin ✓ Decision gates, not just reviews **Schedule integration prevents late surprises**

## Slide 12: Technical Assessment & Control - Earned Value Management
How do you KNOW if your project is on track? Earned Value Management (EVM).
EVM Basics:
Three key values: — PV (Planned Value): Budgeted cost for scheduled work
EV (Earned Value): Budgeted cost for completed work
AC (Actual Cost): Actual cost incurred for completed work
Two key metrics: — SV (Schedule Variance) = EV - PV — Positive: Ahead of schedule
Negative: Behind schedule
CV (Cost Variance) = EV - AC — Positive: Under budget
Negative: Over budget
Two key indices: — SPI (Schedule Performance Index) = EV / PV — > 1.0: Ahead
< 1.0: Behind
CPI (Cost Performance Index) = EV / AC — > 1.0: Under budget
< 1.0: Over budget
ADAS Example at Month 12:
Planned: Should have completed 40% of work (PV = $4M)
Earned: Actually completed 30% of work (EV = $3M)
Actual Cost: Spent $3.5M (AC = $3.5M)
Analysis: — SV = $3M - $4M = -$1M (behind schedule)
CV = $3M - $3.5M = -$0.5M (over budget)
SPI = 3/4 = 0.75 (25% behind schedule)
CPI = 3/3.5 = 0.86 (14% over budget)
Forecast: — EAC (Estimate at Completion) = BAC / CPI = $10M / 0.86 = $11.6M
Expected overrun: $1.6M
With EVM, ADAP problems would have been visible at Month 12, not Month 24.
Automotive standard: EVM required for programs >$10M (ISO 21500)
PPT Content:
TECHNICAL CONTROL: EARNED VALUE MANAGEMENT (EVM) Key Values: • PV (Planned Value): Budget for scheduled work • EV (Earned Value): Budget for completed work • AC (Actual Cost): Actual cost incurred Metrics: • SV = EV - PV (schedule variance) • CV = EV - AC (cost variance) • SPI = EV/PV (schedule index) • CPI = EV/AC (cost index) ADAS Example (Month 12): PV = $4M | EV = $3M | AC = $3.5M → SPI = 0.75 (25% behind) → CPI = 0.86 (14% over budget) → Forecast: $1.6M overrun **EVM makes problems visible early** Tools: MS Project, Primavera, custom dashboards

## Slide 13: Decision Management - Decision Gates
Decision Management is critical. Let's formalize it.
ISO/IEC 15288 Decision Management Process: — Prepare for decisions
Analyze decision information
Make decisions
Manage decisions
Automotive Stage-Gate Process:
Gate 0: Concept — Decision: Pursue this system concept?
Inputs: Market analysis, feasibility study, business case
Criteria: Strategic fit, ROI > 15%, technical feasibility
Outputs: Go/No-Go, funding for requirements phase
Gate 1: Requirements Review — Decision: Requirements complete and stable?
Inputs: Requirements document, stakeholder signoff, CONOPS
Criteria: 100% traceability, < 5% TBD items, customer approval
Outputs: Freeze requirements baseline, proceed to architecture
Gate 2: Architecture Review — Decision: Architecture viable and approved?
Inputs: Architecture description, interface specs, trade studies
Criteria: Meets all requirements, passes safety analysis, cost within target
Outputs: Freeze architecture baseline, proceed to detailed design
Gate 3: Design Review (Critical Design Review - CDR) — Decision: Design ready for implementation?
Inputs: Detailed designs, simulations, prototype results
Criteria: All interfaces defined, V&V plan approved, manufacturing feasible
Outputs: Freeze design baseline, proceed to implementation
Gate 4: System Test Readiness Review — Decision: System ready for full integration?
Inputs: Subsystem test results, integration test plan
Criteria: All subsystems verified, integration environment ready
Outputs: Proceed to system integration
Gate 5: Production Readiness Review — Decision: Release to production?
Inputs: V&V results, certification evidence, field trial data
Criteria: All requirements verified, safety certification, customer acceptance
Outputs: Release to manufacturing
Key principles: — Gates are GO/NO-GO decisions, not reviews
Criteria defined in advance, objective
Cross-functional decision boards
Decisions documented and tracked
ADAP failure: Architecture decisions made without gate criteria, reversed multiple times.
PPT Content:
DECISION MANAGEMENT: STAGE-GATE PROCESS Automotive Development Gates: Gate 0: Concept → Pursue? Criteria: Strategic fit, ROI, feasibility Gate 1: Requirements Review → Complete? Criteria: Traceability, stability, approval Gate 2: Architecture Review → Viable? Criteria: Meets requirements, safe, cost Gate 3: Critical Design Review → Ready? Criteria: Interfaces defined, V&V planned Gate 4: System Test Readiness → Integrate? Criteria: Subsystems verified, env ready Gate 5: Production Readiness → Release? Criteria: Verified, certified, accepted Principles: ✓ GO/NO-GO decisions (not just reviews) ✓ Objective criteria (defined in advance) ✓ Cross-functional boards ✓ Documented & tracked **Gates prevent uncontrolled changes**

## Slide 14: Decision Management - Decision Frameworks
Beyond gates, we need frameworks for technical decisions. Two essential tools:
TOOL 1: Decision Matrix (Pugh Matrix)
Use case: Selecting sensor architecture for ADAS
Alternatives: — A: Radar + Camera
B: Radar + Camera + Lidar
C: Camera-only (Tesla approach)
D: Radar + Ultrasonic
Criteria (weighted): — Cost (20%): Capital + lifecycle
Range (25%): Detection distance
Weather robustness (20%): Rain, fog, snow
Accuracy (15%): Position ±cm
Redundancy (10%): Fault tolerance
Complexity (10%): Integration effort
Scoring (1-5 scale):
| Criterion | Weight | A | B | C | D |
|-----------|--------|---|---|---|---|
| Cost | 20% | 4 | 2 | 5 | 4 |
| Range | 25% | 4 | 5 | 3 | 3 |
| Weather | 20% | 4 | 5 | 2 | 4 |
| Accuracy | 15% | 3 | 5 | 3 | 2 |
| Redundancy | 10% | 3 | 5 | 1 | 2 |
| Complexity | 10% | 4 | 2 | 5 | 4 |
| Total | 100% | 3.75 | 4.15 | 3.25 | 3.25 |
Result: Option B (Radar+Camera+Lidar) wins with 4.15 weighted score
TOOL 2: Real Options Analysis
Use case: When to freeze architecture?
Options: — Option 1: Freeze now (Month 6) → Minimize rework
Option 2: Defer to Month 9 → Wait for sensor tech maturity
Analysis: — Value of waiting: New sensor available Month 8, 30% better performance
Cost of waiting: 3-month schedule slip, $500K holding cost
Probability new sensor works: 70%
Expected value: — Freeze now: $10M system value
Wait: 0.7 × $13M + 0.3 × $10M - $0.5M = $11.6M
Decision: Wait for new sensor (higher expected value)
Key: Both frameworks require:
Defined criteria
Quantitative scoring
Stakeholder agreement
Documentation
This prevents the ADAP ad-hoc decision problem.
PPT Content:
DECISION FRAMEWORKS: STRUCTURED APPROACHES TOOL 1: Decision Matrix (Pugh Matrix) Example: ADAS Sensor Selection Alternatives: Radar+Cam, R+C+Lidar, Cam-only Criteria: Cost, range, weather, accuracy Weighted scoring → Quantitative comparison Result: Radar+Camera+Lidar (4.15 weighted score) TOOL 2: Real Options Analysis Example: Architecture Freeze Timing Option 1: Freeze Month 6 → $10M value Option 2: Wait Month 9 → $11.6M expected value Decision: Wait (higher EV) Framework Requirements: ✓ Defined criteria ✓ Quantitative scoring ✓ Stakeholder agreement ✓ Documentation **Prevents ad-hoc decision chaos**

## Slide 15: Measurement - Technical Performance Measures (TPMs)
You can't control what you don't measure. Technical Performance Measures (TPMs):
TPM Definition (INCOSE):
'Metrics that assess system characteristics and progress toward meeting technical requirements'
Three types of TPMs:
1. Progress TPMs (How much done?)
Requirements completion: % verified and validated
Design maturity: % components at CDR
Test completion: % test cases passed
2. Performance TPMs (Does it meet specs?)
Detection range: Actual vs required 150m
Response latency: Actual vs required 200ms
Reliability: MTBF actual vs required 10,000 hrs
3. Quality TPMs (Is it good?)
Defect density: Defects per 1000 LOC
Rework rate: % requirements changed
Test pass rate: % tests passing first time
ADAS Example TPM Dashboard:
TPM 1: Detection Range — Target: 150m ± 5m
Current: 142m (Month 18 prototype)
Trend: Improving (was 135m Month 15)
Status: Yellow (not yet meeting target)
Action: Algorithm tuning, sensor calibration
TPM 2: Response Latency — Target: < 200ms
Current: 185ms (Month 18)
Trend: Stable
Status: Green (meeting target)
Action: Continue monitoring
TPM 3: Requirements Stability — Target: < 5% changes after Month 6
Current: 12% changed Month 6-12
Trend: Worsening
Status: Red (excessive churn)
Action: Requirements freeze enforcement, change board
TPM 4: Test Pass Rate — Target: > 90% first-time pass
Current: 75% (Month 20)
Trend: Improving (was 65% Month 18)
Status: Yellow (improving but below target)
Action: Root cause analysis of failures
TPM Best Practices: — 5-10 TPMs per project (not 50+)
Leading indicators (predict problems) + lagging indicators (measure results)
Weekly review for critical TPMs
Trend analysis (not just current value)
Automated collection where possible
ADAP failure: No TPMs. Used subjective 'percent complete' only.
PPT Content:
MEASUREMENT: TECHNICAL PERFORMANCE MEASURES (TPMs) Three TPM Types: 1. PROGRESS TPMs (How much done?) • Requirements verified % • Design maturity % • Test completion % 2. PERFORMANCE TPMs (Meets specs?) • Detection range: 142m vs 150m target • Latency: 185ms vs 200ms target • Reliability: MTBF tracking 3. QUALITY TPMs (Is it good?) • Defect density • Rework rate: 12% (Red - too high) • Test pass rate: 75% (Yellow) TPM Dashboard: 5-10 key measures ✓ Leading + lagging indicators ✓ Weekly review ✓ Trend analysis ✓ Automated collection **TPMs make technical progress objective**

## Slide 16: Configuration Management - Baselines and Change Control
Configuration Management (CM) prevents the chaos of 'multiple versions in use.'
CM Purpose (ISO/IEC 15288): — Establish and maintain integrity of all outputs
Control changes to baselines
Ensure everyone works to same version
ADAS Configuration Items: — Requirements specifications
Architecture descriptions
Interface control documents
Design models and drawings
Source code
Test procedures and results
Calibration data
Baseline Concept:
Baseline = Approved version serving as basis for further development
ADAS Baseline Sequence:
Functional Baseline (Month 6): — Requirements specification v1.0 APPROVED
Stakeholder signoff
Changes require CCB approval
Allocated Baseline (Month 12): — Architecture description v1.0 APPROVED
Interface specifications v1.0 APPROVED
Requirements v1.0 frozen (changes only via CCB)
Design Baseline (Month 18): — Detailed designs v1.0 APPROVED
All baselines frozen
Emergency changes only via CCB
Product Baseline (Month 30): — Production release v1.0
All artifacts frozen
Customer-approved changes only
Change Control Board (CCB):
Purpose: Evaluate and approve/reject changes to baselines
Membership: — Chief Engineer (chair)
Systems engineering lead
Hardware, software, test leads
Project manager
Customer representative (for product baseline)
CCB Process:
Change request submitted (anyone can submit)
Impact analysis (SE team)
Technical impact (requirements, architecture, interfaces)
Cost impact ($, resources)
Schedule impact (days)
Risk impact (new risks introduced?)
CCB reviews impact analysis
Decision: Approve, defer, or reject
If approved: Baseline updated, all teams notified
Example Change Request (Month 14):
CR-045: Change radar sensor from 77 GHz to 79 GHz
Justification: New 79 GHz sensor available, 20% better resolution
Impact Analysis: — Technical: Requires new antenna design, FCC re-certification
Cost: +$150K (sensor, certification)
Schedule: +6 weeks (antenna redesign, test)
Risk: Medium (new sensor less mature)
CCB Decision: DEFER to next generation
Rationale: Schedule impact unacceptable, risk too high for current program
This is how you prevent ADAP's 'multiple baselines' problem.
Tools: Git (code), DOORS (requirements), PLM systems (hardware), Jama, Polarion
PPT Content:
CONFIGURATION MANAGEMENT: BASELINES & CHANGE CONTROL Configuration Items (ADAS): • Requirements, architecture, interfaces • Design, code, tests, calibration Baseline Evolution: Month 6: Functional (requirements v1.0) Month 12: Allocated (architecture v1.0) Month 18: Design (detailed design v1.0) Month 30: Product (release v1.0) Change Control Board (CCB): Members: Chief Eng, SE lead, tech leads, PM Process: 1. Change request submitted 2. Impact analysis (tech, cost, schedule, risk) 3. CCB review & decision 4. Update baseline, notify teams Example: Change radar 77→79 GHz Impact: +$150K, +6 weeks, medium risk Decision: DEFER (too risky mid-program) **CCB prevents uncontrolled changes** Tools: Git, DOORS, PLM, Jama, Polarion

## Slide 17: Information Management - Data Architecture
Information Management: ensuring right information to right people at right time.
ISO/IEC 15288 Information Management: — Generate information items
Store and retrieve information
Maintain information integrity
Distribute information
ADAS Information Architecture:
Layer 1: Requirements Information — Tool: IBM DOORS, Jama Connect
Stakeholder requirements
System requirements
Subsystem requirements
Verification traces
Access: All SE team, read-only for broader team
Layer 2: Design Information — Tool: SysML tool (Cameo, Rhapsody), CAD (CATIA, NX)
Architecture models
Detailed designs
Interface specifications
Simulation results
Access: Design team read-write, SE team read-only
Layer 3: Implementation Information — Tool: Git, Bitbucket, SVN
Source code
Build scripts
Calibration data
Access: Dev team read-write, version controlled
Layer 4: Verification Information — Tool: Test management (TestRail, Zephyr), JIRA
Test plans, cases, procedures
Test results and logs
Defect reports
V&V evidence
Access: Test team read-write, SE review
Layer 5: Project Information — Tool: MS Project, Primavera, SharePoint
WBS, schedules, budgets
Status reports, metrics
Risk register
Decision logs
Access: PM read-write, stakeholders read
Layer 6: Document Management — Tool: SharePoint, Documentum, PLM
Specifications, plans, reports
Presentations, drawings
Baselined documents
Access: Role-based, version controlled
Information Integration:
Challenge: Data in 10+ tools, risk of disconnection
Solution: Integration architecture
DOORS ↔ SysML: Requirements ↔ Architecture trace
SysML ↔ CAD: Logical ↔ Physical trace
DOORS ↔ Test Mgmt: Requirements ↔ Tests trace
All → PLM: Centralized baseline repository
Key principles: — Single source of truth for each artifact
Automated synchronization where possible
Clear ownership (who maintains what)
Version control for all artifacts
Access control based on roles
ADAP failure: No information architecture, teams used different tools/versions.
PPT Content:
INFORMATION MANAGEMENT: DATA ARCHITECTURE Six Information Layers (ADAS): 1. Requirements (DOORS, Jama) • Stakeholder, system, subsystem reqs • Verification traces 2. Design (SysML, CAD) • Architecture, detailed designs • Interfaces, simulations 3. Implementation (Git, SVN) • Source code, calibrations • Build scripts 4. Verification (TestRail, JIRA) • Test plans, results, defects • V&V evidence 5. Project (MS Project, SharePoint) • WBS, schedules, metrics • Risks, decisions 6. Documents (SharePoint, PLM) • Specs, plans, reports • Baselined documents Integration: DOORS↔SysML↔CAD↔Test→PLM Principles: ✓ Single source of truth ✓ Automated sync ✓ Version control ✓ Role-based access **Prevents tool/version chaos**

## Slide 18: Risk Management Revisited - Technical Risk Focus
We covered risk management in Session 9. Let's focus on TECHNICAL risks specific to management processes.
Technical Risks in ADAS Development:
Risk 1: Technology Maturity Risk — Description: New 79 GHz radar sensor unproven in automotive
Probability: Medium (40%)
Impact: High (6-month delay, $2M)
Mitigation: Parallel development of 77 GHz backup
Trigger: If 79 GHz fails qualification by Month 12, switch to 77 GHz
Owner: Hardware lead
Risk 2: Integration Complexity Risk — Description: 5 subsystems, 15+ interfaces, integration may fail
Probability: High (60%)
Impact: High (3-month delay)
Mitigation: Incremental integration from Month 15, HIL testing from Month 12
Trigger: If integration issues found, add integration sprint
Owner: Integration lead
Risk 3: Requirements Instability Risk — Description: Customer changes requirements after Month 6 baseline
Probability: Medium (50%)
Impact: Medium ($500K, 2-month delay per change)
Mitigation: Strict CCB process, customer signoff at Gate 1
Trigger: Reject changes unless critical safety issue
Owner: Chief engineer
Risk 4: Resource Availability Risk — Description: Key experts pulled to other projects
Probability: Medium (40%)
Impact: Medium (schedule slip, quality issues)
Mitigation: Cross-training, knowledge documentation, portfolio prioritization
Trigger: If expert unavailable >2 weeks, escalate to portfolio management
Owner: Project manager
Risk 5: Verification Coverage Risk — Description: Insufficient test scenarios, defects escape to field
Probability: Low (20%)
Impact: Critical (recall, reputation)
Mitigation: 100% requirements coverage, edge case analysis, field trials
Trigger: If test pass rate <90%, extend V&V phase
Owner: V&V lead
Risk Management Integration: — Risks reviewed monthly at project status meeting
Top 5 risks reported to senior management
Risk reserve in budget (15-20%)
Risk triggers monitored via TPMs
ADAP failure: Risks identified but not actively managed, no trigger-based mitigation.
PPT Content:
RISK MANAGEMENT: TECHNICAL RISK FOCUS Top Technical Risks (ADAS): Risk 1: Technology Maturity • New sensor unproven • P: 40% | I: High (6mo, $2M) • Mitigation: Parallel backup development Risk 2: Integration Complexity • 5 subsystems, 15+ interfaces • P: 60% | I: High (3mo delay) • Mitigation: Incremental integration, HIL Risk 3: Requirements Instability • Customer changes post-baseline • P: 50% | I: Medium ($500K, 2mo) • Mitigation: CCB, strict gate process Risk 4: Resource Availability • Experts pulled to other projects • P: 40% | I: Medium (schedule, quality) • Mitigation: Cross-train, portfolio priority Risk 5: Verification Coverage • Insufficient test scenarios • P: 20% | I: Critical (recall) • Mitigation: 100% coverage, edge cases **Active monitoring via TPMs, trigger-based response**

## Slide 19: Quality Assurance - Process Compliance
Quality Assurance (QA) ensures processes are followed and products meet standards.
QA vs QC (Quality Control): — QA (Assurance): Process-focused, preventive
Are we following the right processes?
Reviews, audits, training
QC (Control): Product-focused, detective
Is the product correct?
Testing, inspection, measurement
Both needed. Today we focus on QA.
QA Activities in ADAS Development:
Phase 1: Requirements (Months 0-6) — Process QA: — Requirements review checklist compliance
Traceability audit (stakeholder → system requirements)
Template compliance (IEEE 29148)
Gate 1 QA Check: — 100% requirements in DOORS?
100% traceability to stakeholders?
All TBDs resolved?
Phase 2: Architecture (Months 6-12) — Process QA: — Architecture review board
Trade study documentation audit
Interface specification compliance
Gate 2 QA Check: — All requirements allocated to architecture?
Interface specs complete and approved?
Safety analysis (FMEA) completed?
Phase 3: Design (Months 12-18) — Process QA: — Design review checklists
Code review compliance (MISRA C)
Configuration management audit
Gate 3 QA Check: — All designs reviewed and approved?
Code meets coding standards?
All baselines in CM system?
Phase 4: Integration & V&V (Months 18-30) — Process QA: — Test procedure review
V&V plan compliance audit
ISO 26262 compliance assessment
Gate 4 QA Check: — 100% requirements verified?
All test evidence documented?
Safety certification complete?
QA Standards for Automotive: — ISO 26262: Functional safety QA requirements
Automotive SPICE: Process capability assessment
ASPICE Level 3 target: Defined and established process
QA Independence: — QA team reports to quality organization, not project manager
Prevents 'pressure to pass' conflicts
Authority to stop project at gate if criteria not met
ADAP failure: QA existed but no authority, gates became 'rubber stamps.'
PPT Content:
QUALITY ASSURANCE: PROCESS COMPLIANCE QA vs QC: • QA: Process-focused, preventive (right processes?) • QC: Product-focused, detective (right product?) QA Activities by Phase (ADAS): Phase 1: Requirements • Review checklist compliance • Traceability audit • Gate 1: 100% reqs traced, TBDs resolved Phase 2: Architecture • Architecture review • Trade study audit • Gate 2: Reqs allocated, interfaces complete Phase 3: Design • Design reviews, code reviews • CM audit • Gate 3: Designs approved, code compliant Phase 4: V&V • V&V plan compliance • ISO 26262 assessment • Gate 4: 100% verified, certified QA Standards: ISO 26262, ASPICE Level 3 QA Independence: Reports to quality org, not PM **Authority to stop project if criteria not met**

## Slide 20: Continuous Improvement - Lessons Learned
Technical management includes organizational learning. The Lessons Learned process.
Lessons Learned Purpose: — Capture what worked / didn't work
Share knowledge across projects
Improve processes and practices
Prevent repeating mistakes
Lessons Learned Process:
Step 1: Capture (Throughout Project) — Weekly team retrospectives
Post-milestone reviews (after each gate)
Issue logs (problems encountered)
Innovation logs (creative solutions)
Step 2: Document (Structured Format) — Situation: What was the context?
Action: What did we do?
Result: What happened?
Recommendation: What should future projects do?
Example Lesson from ADAP:
Lesson #23: Interface Freeze Timing — Situation: ADAP changed CAN message definitions at Month 14 (after subsystem development started)
Action: Teams had to rework interface code, regression test
Result: 6-week delay, $800K rework cost, integration issues
Root Cause: No formal interface freeze date
Recommendation: Establish interface freeze at Gate 2 (architecture review). Include in technical plan. CCB approval required for any interface changes after freeze.
Process Change: Added 'Interface Freeze' milestone to project plan template
Step 3: Review and Approve — Monthly lessons learned review meeting
Engineering review board validates
Classify: Organization-wide vs project-specific
Step 4: Disseminate — Lessons learned database (searchable)
Training materials updated
Briefing for new projects
Project plan templates updated
Step 5: Apply — New projects review relevant lessons during planning
Checklists include common pitfalls
Metrics track whether lessons applied
Automotive OEM Example: — BMW lessons learned system: 10,000+ lessons captured
Search by: Technology, issue type, project phase
Mandatory review before project kickoff
Tracked: Did project review lessons? Did they apply them?
ADAP failure: No lessons learned from previous ADAS project. Repeated same integration mistakes.
Key: Lessons learned must be ACTIONABLE and APPLIED, not just documented.
PPT Content:
CONTINUOUS IMPROVEMENT: LESSONS LEARNED Process Steps: 1. CAPTURE (Throughout) • Weekly retrospectives • Post-gate reviews • Issue/innovation logs 2. DOCUMENT (Structured) • Situation, Action, Result • Root cause, Recommendation 3. REVIEW & APPROVE • Monthly LL review • Classify: Org-wide vs project 4. DISSEMINATE • Searchable database • Training materials • Project templates 5. APPLY • Review before kickoff • Checklist pitfalls • Track application Example: ADAP Interface Freeze Lesson • Changed CAN at Month 14 → 6-week delay, $800K • Recommendation: Freeze interfaces at Gate 2 • Process change: Added to plan template **BMW: 10,000+ lessons, mandatory review** **Lessons must be APPLIED, not just captured**

## Slide 21: Part 1 Summary - Technical Management Processes
Let's consolidate Part 1: Technical Management Processes.
We covered 8 processes from ISO/IEC 15288:
1. Project Planning — Work Breakdown Structure (WBS)
Integrated Master Schedule (IMS)
Resource allocation
Purpose: Define all work, sequence, resources
2. Project Assessment & Control — Earned Value Management (EVM)
Status tracking
Corrective action
Purpose: Monitor progress, control execution
3. Decision Management — Stage-gate process
Decision frameworks (Pugh, real options)
CCB for changes
Purpose: Structured, traceable decisions
4. Risk Management — Technical risk identification
Mitigation planning
Trigger-based response
Purpose: Proactive uncertainty management
5. Configuration Management — Baselines (functional, allocated, design, product)
Change control board
Version management
Purpose: Maintain integrity, control changes
6. Information Management — Multi-layer data architecture
Tool integration
Access control
Purpose: Right info to right people at right time
7. Measurement — Technical Performance Measures (TPMs)
Progress, performance, quality metrics
Trend analysis
Purpose: Objective visibility into technical status
8. Quality Assurance — Process compliance audits
Gate criteria enforcement
Independent authority
Purpose: Ensure processes followed, standards met
How These Prevented ADAP Failure: — Planning → Would have defined integration milestones
Control → Would have detected schedule slip at Month 12
Decision Mgmt → Would have prevented architecture churn
Configuration → Would have prevented multiple baselines
Measurement → Would have shown requirements instability
QA → Would have enforced gate criteria
These 8 processes are the MANAGEMENT FOUNDATION for technical processes.
Now Part 2: Enabling processes that support everything.
PPT Content:
PART 1 SUMMARY: TECHNICAL MANAGEMENT PROCESSES 8 ISO/IEC 15288 Processes: 1. Project Planning → WBS, schedule, resources 2. Project Assessment & Control → EVM, status, corrective action 3. Decision Management → Gates, frameworks, CCB 4. Risk Management → Identify, mitigate, monitor 5. Configuration Management → Baselines, change control 6. Information Management → Data architecture, integration 7. Measurement → TPMs, metrics, trends 8. Quality Assurance → Audits, compliance, gates **These prevent ADAP-type failures** **Management foundation for technical processes** → Next: Enabling processes (organizational)

## Slide 22: Organizational Enabling Processes - Overview
Part 2: Organizational Project-Enabling Processes. These operate at the ORGANIZATIONAL level, not project level.
ISO/IEC 15288 defines 5 enabling processes:
1. Life Cycle Model Management — Define and maintain organizational SE lifecycle models
Tailor models for different project types
Example: V-Model for safety-critical, Agile for infotainment
Operates at: Enterprise/organization level
Enables: Consistent process across projects
2. Infrastructure Management — Provide and maintain SE infrastructure
Tools, facilities, test environments
Example: HIL lab, DOORS licenses, CAD workstations
Operates at: Organization level
Enables: Technical work (can't do SE without tools)
3. Portfolio Management — Strategically manage portfolio of projects
Resource allocation across projects
Prioritization and alignment
Example: Fund ADAS over infotainment upgrade
Operates at: Executive level
Enables: Strategic alignment, resource optimization
4. Human Resource Management — Acquire, develop, maintain competent workforce
Training, competency development
Example: SysML training, safety certification
Operates at: HR + Engineering management
Enables: Skilled workforce
5. Quality Management — Organizational quality policies and processes
Quality system (ISO 9001, ASPICE)
Example: ASPICE Level 3 process framework
Operates at: Quality organization
Enables: Consistent quality across organization
Key difference from technical management: — Technical management: Project-level, specific to one system
Enabling processes: Organization-level, support all projects
Today we focus on three critical enabling processes: — Knowledge Management (often missing)
Portfolio Management (resource conflicts)
Infrastructure Management (tool chaos)
These are often the ROOT CAUSE of project failures, not the projects themselves.
PPT Content:
ORGANIZATIONAL ENABLING PROCESSES (5) 1. Life Cycle Model Management • Define org SE lifecycle • Tailor for project types 2. Infrastructure Management • Tools, facilities, environments • SE infrastructure provision 3. Portfolio Management • Strategic project management • Resource allocation & priority 4. Human Resource Management • Workforce development • Training, competency 5. Quality Management • Org quality system • ISO 9001, ASPICE **Difference:** • Technical mgmt: Project-level • Enabling: Organization-level (support all projects) **Today's focus: Knowledge, Portfolio, Infrastructure** **Root cause of many project failures**

## Slide 23: Knowledge Management - Organizational Learning
Knowledge Management is the most neglected enabling process. Yet critical.
Knowledge Management Purpose (ISO/IEC 15288):
'Ensure that individual, project, and organizational knowledge is created, collected, retained, shared, and applied to meet objectives'
Why Knowledge Management Matters:
Problem 1: Expert Dependency — Critical knowledge in expert's heads
Expert leaves → knowledge lost
ADAP example: Integration expert retired, new person repeated mistakes
Problem 2: Knowledge Silos — Radar team knows radar, camera team knows camera
No shared understanding of sensor fusion
Integration fails due to assumptions mismatch
Problem 3: Repeated Mistakes — Previous project made integration error
Lesson not documented or shared
New project repeats same error
Problem 4: Slow Onboarding — New engineers take 6-12 months to become productive
No structured knowledge transfer
Mentorship ad-hoc
Knowledge Management Framework:
1. Knowledge Creation — Research and development
Innovation and experimentation
Problem-solving
Example: Develop new sensor fusion algorithm
2. Knowledge Capture — Documentation (design documents, reports)
Lessons learned (from projects)
Expert interviews (before retirement)
Communities of practice
Example: Document algorithm in wiki, record expert video
3. Knowledge Organization — Taxonomy and classification
Searchable repositories
Metadata and tagging
Example: Knowledge base with categories: Sensors, Fusion, Control, V&V
4. Knowledge Sharing — Training programs
Brown bag sessions (lunch & learn)
Communities of practice (CoP)
Mentoring programs
Example: Monthly 'Sensor Fusion CoP' meeting
5. Knowledge Application — Reuse in new projects
Best practices implementation
Decision support
Example: New ADAS project uses previous fusion algorithm
6. Knowledge Retention — Critical knowledge identification
Succession planning
Knowledge transfer before departures
Example: Expert creates training course before retiring
Automotive OEM Example - Toyota:
Toyota Technical Skills Institute: — Captures expert knowledge in manufacturing, design, SE
Video libraries of expert techniques
Apprenticeship programs (master-apprentice)
'Toyota Way' knowledge base
Result: Knowledge retained across generations
Knowledge Management Tools: — Wiki: Confluence, SharePoint wiki
Document repository: SharePoint, Documentum
Lessons learned DB: Custom or commercial
Expert directory: Skills database
Communities: Yammer, Slack channels
ADAP could have avoided failures with: — Documented integration lessons from previous project
Sensor fusion community of practice
Expert knowledge captured before retirement
PPT Content:
KNOWLEDGE MANAGEMENT: ORGANIZATIONAL LEARNING Purpose: Create, collect, retain, share, apply knowledge Four Problems: 1. Expert dependency (knowledge lost) 2. Knowledge silos (teams disconnected) 3. Repeated mistakes (lessons not shared) 4. Slow onboarding (6-12 months) KM Framework (6 Steps): 1. Create: R&D, innovation, problem-solving 2. Capture: Docs, lessons, expert interviews 3. Organize: Taxonomy, repositories, metadata 4. Share: Training, CoP, mentoring 5. Apply: Reuse, best practices, decisions 6. Retain: Succession planning, transfer Example: Toyota Technical Skills Institute • Video expert techniques • Apprenticeship programs • 'Toyota Way' knowledge base • Result: Multi-generational knowledge Tools: Wiki, doc repos, lessons DB, expert directory **KM prevents knowledge loss and repeated errors**

## Slide 24: Portfolio Management - Strategic Alignment
Portfolio Management: Managing the RIGHT mix of projects, not just managing projects right.
Portfolio Management Purpose (ISO/IEC 15288):
'Initiate and sustain necessary, sufficient, and suitable projects to meet strategic objectives'
The Portfolio Challenge:
Scenario: Automotive OEM has 20 active projects: — 5 ADAS projects (autonomous driving, safety features)
6 Powertrain projects (electrification, efficiency)
4 Infotainment projects (connectivity, UX)
3 Body systems (comfort, convenience)
2 Manufacturing (production line upgrades)
Resources: — 150 systems engineers (not 500)
$500M R&D budget (not unlimited)
12 HIL test benches (shared across projects)
50 senior experts (heavily in demand)
Portfolio Questions:
Which projects to fund? Which to kill?
How to allocate 150 engineers across 20 projects?
What if ADAS Project A needs expert currently on Powertrain Project B?
If budget cut 20%, which projects suffer?
This is Portfolio Management.
Portfolio Management Process:
Step 1: Strategic Alignment — Company strategy: 'Leader in autonomous driving by 2028'
Portfolio analysis: Are projects aligned?
ADAS projects: High alignment
Infotainment projects: Medium alignment
Body systems: Low alignment (unless differentiation)
Step 2: Portfolio Categorization
Three categories:
Strategic (Must-Have): — Aligned with core strategy
Example: Level 3 autonomous ADAS (strategic commitment)
Resource priority: Highest
Operational (Keep-Running): — Sustaining current products
Example: Infotainment updates for current models
Resource priority: Medium
Exploratory (Future): — Innovation, R&D, new technologies
Example: Lidar sensor research
Resource priority: Opportunistic
Step 3: Portfolio Prioritization
Prioritization Matrix: Value vs Effort
High Value, Low Effort (Do First): — ADAS Project A: Safety feature (regulatory requirement), reuses existing platform
Priority: 1
High Value, High Effort (Strategic Investment): — ADAS Project B: Full autonomous stack, new technology
Priority: 2 (if resources available)
Low Value, Low Effort (Do If Capacity): — Infotainment Project C: Minor UX update
Priority: 3
Low Value, High Effort (Kill or Defer): — Body Project D: Luxury feature, limited market
Priority: 4 (consider killing)
Step 4: Resource Allocation
Resource pool: 150 SE engineers
Allocation: — Strategic projects (ADAS): 80 engineers (53%)
Operational projects: 50 engineers (33%)
Exploratory projects: 20 engineers (13%)
If conflict: Strategic projects get priority
Step 5: Portfolio Balancing
Balance across: — Technology domains: ADAS, powertrain, infotainment (not all in one area)
Risk profile: High-risk innovation + low-risk sustaining
Timeline: Short-term (12mo) + long-term (5yr) projects
Resource types: Don't overload specific experts
Step 6: Portfolio Monitoring
Quarterly portfolio review: — Project status (on-track? struggling?)
Resource utilization (bottlenecks? idle?)
Strategic alignment (still aligned?)
Kill/defer decisions (shut down failing projects)
Portfolio Governance: — Portfolio Board: CTO, VP Engineering, CFO, business unit heads
Meets: Quarterly (or monthly if dynamic)
Authority: Start, stop, redirect projects
ADAP example: Would have prioritized ADAP vs competing projects, allocated experts accordingly
Result: Right projects get right resources at right time.
PPT Content:
PORTFOLIO MANAGEMENT: STRATEGIC ALIGNMENT Purpose: Right mix of projects for strategy Portfolio Challenge: 20 projects, 150 engineers, $500M budget → Which to fund? How to allocate? PM Process: 1. Strategic Alignment • Strategy: Leader in autonomous • ADAS: High | Infotainment: Med | Body: Low 2. Categorization • Strategic (must-have): ADAS • Operational (sustain): Updates • Exploratory (future): R&D 3. Prioritization (Value vs Effort) • High V, Low E: Do first • High V, High E: Strategic investment • Low V, High E: Kill or defer 4. Resource Allocation • Strategic: 53% | Operational: 33% | Explore: 13% 5. Balancing • Technology, risk, timeline, resources 6. Monitoring • Quarterly review, kill/defer decisions **Governance: Portfolio Board (CTO, VPs, CFO)** **Right projects, right resources, right time**

## Slide 25: Infrastructure Management - Tools and Environments
Infrastructure Management: Providing the tools and environments for SE work.
Infrastructure Management Purpose (ISO/IEC 15288):
'Provide infrastructure required to support technical and management processes'
What is SE Infrastructure?
Category 1: Software Tools — Requirements management: IBM DOORS, Jama Connect, Polarion
Architecture/design: SysML tools (Cameo, Rhapsody), MATLAB/Simulink
Configuration management: Git, SVN, PLM (Siemens Teamcenter)
Project management: MS Project, Primavera, JIRA
V&V: CANoe, dSPACE, test management (TestRail)
Document management: SharePoint, Documentum
Category 2: Hardware Infrastructure — Workstations: High-performance for simulation
Servers: Compute clusters for analysis
Network: High-speed for data transfer
Storage: Centralized repositories (NAS, SAN)
Category 3: Test and Integration Facilities — Hardware-in-Loop (HIL) benches: 10-20 setups for ADAS testing
Software-in-Loop (SIL) environments: Virtual testing
Vehicle test fleet: Instrumented vehicles
Environmental chambers: Temperature, vibration, EMC
Proving grounds: Test tracks
Category 4: Development Environments — Build systems: Continuous integration (Jenkins, GitLab CI)
Simulation environments: CARLA, VTD for autonomous
Calibration tools: ETAS INCA, Vector CANape
Infrastructure Challenges:
Challenge 1: Tool Sprawl — 30+ tools used across organization
Poor integration between tools
Duplicate data entry
Solution: Tool integration architecture, single-source-of-truth principle
Challenge 2: Version Incompatibility — Team A uses DOORS 9.6, Team B uses DOORS 9.7
Files incompatible, collaboration breaks
Solution: Standardized tool versions, upgrade planning
Challenge 3: License Limitations — 50 DOORS licenses, 80 users
Engineers wait for license availability
Solution: Floating licenses, usage monitoring, capacity planning
Challenge 4: Infrastructure Obsolescence — HIL benches use 10-year-old hardware
Can't support new ECU platforms
Solution: Infrastructure refresh cycles (every 3-5 years)
Challenge 5: Access and Security — Confidential designs must be protected
But collaboration requires sharing
Solution: Role-based access, secure networks, data classification
Infrastructure Management Process:
Plan: — Assess infrastructure needs (tools, facilities)
3-year infrastructure roadmap
Budget allocation (typically 5-10% of R&D budget)
Acquire: — Tool procurement
Facility construction/upgrade
Vendor selection and negotiation
Deploy: — Tool installation and configuration
User training
Support processes
Maintain: — Version upgrades
License management
Technical support
Performance monitoring
Retire: — Tool/facility end-of-life
Data migration
Knowledge transfer
Automotive OEM Example:
BMW Group Tool Infrastructure: — Standardized on Siemens Teamcenter PLM (enterprise-wide)
IBM DOORS for requirements (20,000 users)
CATIA for mechanical design (standard)
100+ HIL benches worldwide
Centralized tool support organization (200 people)
Annual infrastructure investment: €50M
Result: Consistent tooling, global collaboration, reduced training
ADAP example: Would have provided standardized tools, preventing version chaos.
PPT Content:
INFRASTRUCTURE MANAGEMENT: TOOLS & ENVIRONMENTS Purpose: Provide infrastructure for SE processes Four Categories: 1. Software Tools • Requirements (DOORS, Jama) • Design (SysML, Simulink) • CM (Git, PLM), PM (MS Project) • V&V (CANoe, dSPACE) 2. Hardware Infrastructure • Workstations, servers, network, storage 3. Test & Integration Facilities • HIL benches (10-20 setups) • SIL environments, vehicle fleet • Environmental chambers, test tracks 4. Development Environments • Build systems (CI/CD) • Simulation (CARLA, VTD) • Calibration tools Challenges: • Tool sprawl (30+ tools) • Version incompatibility • License limitations • Obsolescence • Access & security Process: Plan → Acquire → Deploy → Maintain → Retire Example: BMW standardized Teamcenter, DOORS, CATIA 100+ HIL benches, €50M/yr investment **Prevents tool chaos, enables collaboration**

## Slide 26: Lifecycle Model Management - Process Tailoring
Life Cycle Model Management: Defining HOW to do systems engineering across the organization.
Lifecycle Model Management Purpose (ISO/IEC 15288):
'Ensure that appropriate life cycle models, processes, and procedures are available for use'
Why Multiple Lifecycle Models?
One-size does NOT fit all:
Project Type A: Safety-Critical ADAS — High complexity, high risk
Regulatory requirements (ISO 26262)
Lifecycle model: V-Model (waterfall-based)
Rationale: Need rigorous documentation, traceability, certification
Project Type B: Infotainment System — Moderate complexity, user-focused
Frequent updates, evolving requirements
Lifecycle model: Agile/Scrum with SE overlay
Rationale: Need flexibility, rapid iteration, user feedback
Project Type C: Exploratory R&D — High uncertainty, innovation-focused
Proof-of-concept, feasibility
Lifecycle model: Spiral model (iterative risk-driven)
Rationale: Need experimentation, learning, pivoting
Project Type D: Platform Reuse — Low complexity, leveraging existing
Incremental changes to proven platform
Lifecycle model: Incremental model
Rationale: Minimize changes, reuse verification
Lifecycle Model Management Process:
Step 1: Define Organizational Lifecycle Models
Model 1: V-Model (Safety-Critical) — Phases: Concept → Requirements → Architecture → Design → Implement → Integrate → V&V
Gates: 5 decision gates with strict criteria
Documents: 20+ mandatory documents (requirements spec, architecture, FMEA, V&V plan, safety case)
Compliance: ISO 26262, ASPICE
Model 2: Agile SE Model (User-Focused) — Sprints: 2-week iterations
SE activities: Requirements in backlog, architecture evolves, continuous V&V
Gates: End-of-sprint reviews, PI planning
Documents: Lightweight (user stories, architecture decision records, test results)
Compliance: Agile Manifesto + ISO/IEC 15288 core processes
Model 3: Spiral Model (R&D) — Cycles: 4-6 risk-driven iterations
SE activities: Prototyping, testing, learning
Gates: Risk review after each cycle
Documents: Minimal (feasibility reports, prototypes)
Step 2: Tailoring Guidelines
Tailoring Criteria: — Project size: <$1M (lightweight), $1-10M (moderate), >$10M (full)
Safety criticality: QM / ASIL A-B (moderate) / ASIL C-D (rigorous)
Novelty: Reuse (incremental) / New development (V-Model) / R&D (Spiral)
Schedule: <6mo (Agile) / 6-24mo (V-Model) / >24mo (Incremental releases)
Tailoring Process:
Project characterization (size, criticality, novelty, schedule)
Select base lifecycle model
Tailor processes (add/remove/modify)
Document tailoring rationale
Approval by engineering review board
Example Tailoring: ADAP (ADAS, ASIL-D, 30-month) — Base model: V-Model
Tailoring:
Add: ISO 26262 safety activities (FMEA, FTA, FMEDA)
Add: Continuous integration (not just gate-based)
Remove: Some documentation for non-safety functions
Result: 'V-Model with Agile Integration' hybrid
Step 3: Process Asset Library
Organizational repository: — Lifecycle model templates
Process descriptions (how-to guides)
Work product templates (requirements spec template, V&V plan template)
Checklists (gate criteria, review checklists)
Training materials
Example: Requirements Engineering Process Asset: — Process description: 'How to do requirements engineering' (10-page guide)
Template: IEEE 29148 requirements specification template
Checklist: Requirements quality checklist (25 items)
Tool guide: 'How to use DOORS' (training slides)
Examples: Sample requirements from previous projects
Step 4: Process Improvement
Continuous improvement: — Lessons learned from projects
Process audits and assessments
Benchmarking with industry
ASPICE assessments
Update models and assets
Automotive OEM Example: Mercedes-Benz — 5 lifecycle models defined (V-Model, Agile SE, Incremental, Spiral, DevOps)
Tailoring guide: 30-page decision tree
Process asset library: 500+ templates and guides
ASPICE Level 3 achieved across organization
Result: Consistent processes, but flexible for project needs.
PPT Content:
LIFECYCLE MODEL MANAGEMENT: PROCESS TAILORING Purpose: Appropriate models, processes, procedures for use Why Multiple Models? Project Type A: Safety-Critical ADAS → V-Model (rigorous, traceable) Project Type B: Infotainment → Agile SE (flexible, iterative) Project Type C: R&D → Spiral (risk-driven, learning) Project Type D: Platform Reuse → Incremental (minimize change) LCM Process: 1. Define Org Models (V, Agile, Spiral, etc.) 2. Tailoring Guidelines • Criteria: Size, safety, novelty, schedule • Process: Characterize → Select → Tailor → Approve 3. Process Asset Library • Templates, guides, checklists, training 4. Process Improvement • Lessons learned, audits, ASPICE Example: Mercedes-Benz 5 models, tailoring guide, 500+ assets, ASPICE L3 **Consistent but flexible processes**

## Slide 27: Complete Process Framework - ISO/IEC 15288
Let's see the COMPLETE ISO/IEC 15288 framework - all 21 processes integrated:
TECHNICAL PROCESSES (8) - Sessions 1-14:
Business or Mission Analysis
Stakeholder Needs and Requirements Definition
System Requirements Definition
Architecture Definition
Design Definition
System Analysis
Implementation
Integration, Verification, Validation, Transition
→ These are the 'WHAT' and 'HOW' of systems engineering.
TECHNICAL MANAGEMENT PROCESSES (8) - Today Part 1:
Project Planning
Project Assessment and Control
Decision Management
Risk Management
Configuration Management
Information Management
Measurement
Quality Assurance
→ These MANAGE technical execution.
ORGANIZATIONAL ENABLING PROCESSES (5) - Today Part 2:
Life Cycle Model Management
Infrastructure Management
Portfolio Management
Human Resource Management
Quality Management (organizational)
→ These ENABLE all processes.
How They Integrate:
Scenario: ADAS Development
Enabling (Before Project Starts): — Portfolio mgmt: Approves ADAS project, allocates budget
Infrastructure: Provides DOORS, HIL benches
Lifecycle: Defines V-Model process for ADAS
HR: Assigns skilled SE engineers
Quality: Establishes ISO 26262 compliance framework
Technical Management (Throughout Project): — Planning: WBS, schedule, resources
Control: EVM tracking, status reviews
Decision: Gate reviews, architecture decisions
Risk: Identify, mitigate technical risks
Configuration: Baseline requirements, architecture
Information: DOORS for reqs, Git for code
Measurement: TPMs for progress, performance
QA: Audits, gate criteria enforcement
Technical (Core SE Work): — Requirements: Define system requirements
Architecture: Design system structure
Design: Detailed subsystem design
Implementation: Build subsystems
Integration: Combine subsystems
Verification: Test against requirements
Validation: Test against needs
The Integration Flow:
Enabling processes provide foundation →
Technical management processes control execution →
Technical processes deliver system →
Back to enabling (lessons learned feed knowledge mgmt)
This is the COMPLETE systems engineering framework.
ISO/IEC 15288 is not just technical processes. It's all 21 processes working together.
Most organizations implement technical processes (8) well.
Many implement some technical management (4-6 of 8).
Few implement enabling processes (0-2 of 5).
Result: Projects struggle despite good technical work.
The lesson of Session 15: All 21 processes are required for SE success.
PPT Content:
COMPLETE ISO/IEC 15288 FRAMEWORK (21 Processes) TECHNICAL PROCESSES (8) • Business, requirements, architecture, design • Analysis, implementation, integration, V&V → WHAT and HOW of SE TECHNICAL MANAGEMENT (8) • Planning, control, decision, risk • Configuration, information, measurement, QA → MANAGE technical execution ORGANIZATIONAL ENABLING (5) • Lifecycle, infrastructure, portfolio • HR, quality management → ENABLE all processes Integration Flow: Enabling (foundation) → Technical Mgmt (control) → Technical (deliver) → Back to Enabling (lessons learned) **All 21 processes required for SE success** Typical Implementation: • Technical: 8/8 (100%) • Mgmt: 4-6/8 (50-75%) • Enabling: 0-2/5 (0-40%) **Gap in enabling processes = root cause of failures**

## Slide 28: Best Practices - Management and Enabling Processes
Let's consolidate best practices for management and enabling processes:
TECHNICAL MANAGEMENT BEST PRACTICES:
Planning & Control:
✓ Develop WBS to 4-6 levels (assignable, estimable)
✓ Define integration milestones early (not just end-of-project)
✓ Use EVM for progress tracking (not subjective % complete)
✓ Reserve 15-20% schedule margin for risks
✓ Weekly status reviews during integration phase
Decision Management:
✓ Define gate criteria in advance (objective, measurable)
✓ Use decision frameworks (Pugh, real options) for major decisions
✓ Document all decisions and rationale
✓ CCB for all baseline changes (requirements, architecture, design)
✓ Impact analysis required for all changes
Measurement:
✓ Define 5-10 key TPMs (progress, performance, quality)
✓ Automate data collection where possible
✓ Trend analysis, not just current values
✓ Leading indicators to predict problems
✓ Weekly TPM review for critical measures
Configuration & Information:
✓ Establish baselines at gates (functional, allocated, design, product)
✓ Single source of truth for each artifact
✓ Tool integration to prevent disconnection
✓ Version control for all work products
✓ Role-based access control
Risk & Quality:
✓ Risk identification at project start, monthly updates
✓ Trigger-based mitigation (not reactive)
✓ Independent QA (reports to quality org, not PM)
✓ Gate authority to stop project if criteria not met
✓ Continuous improvement via lessons learned
ENABLING PROCESS BEST PRACTICES:
Knowledge Management:
✓ Capture lessons at end of each phase (not just end of project)
✓ Structured format (situation, action, result, recommendation)
✓ Searchable repository (by technology, issue, phase)
✓ Mandatory lessons review at project kickoff
✓ Measure application: Did project apply relevant lessons?
Portfolio Management:
✓ Strategic alignment first, then resource allocation
✓ Categorize: Strategic, operational, exploratory
✓ Prioritize using value vs effort matrix
✓ Quarterly portfolio reviews
✓ Kill failing projects (don't let them drag)
Infrastructure Management:
✓ Standardize on organization-wide tools (not team-specific)
✓ 3-5 year infrastructure roadmap
✓ Allocate 5-10% of R&D budget to infrastructure
✓ Centralized tool support organization
✓ Regular tool upgrades (every 2-3 years)
Lifecycle Model Management:
✓ Define 3-5 lifecycle models for different project types
✓ Tailoring guidelines based on size, criticality, novelty
✓ Process asset library (templates, checklists, guides)
✓ ASPICE or CMMI assessment every 2-3 years
✓ Continuous process improvement
Human Resource Management:
✓ Competency model for SE roles (junior, senior, expert)
✓ Training programs: SysML, ISO 26262, ASPICE
✓ Succession planning for critical experts
✓ Cross-training to prevent single-point dependencies
✓ Career development paths for SE professionals
IMPLEMENTATION APPROACH:
Don't implement all at once: — Year 1: Focus on technical management (planning, control, decision, risk, config)
Year 2: Add measurement, QA, information management
Year 3: Add enabling processes (knowledge, portfolio, infrastructure)
Ongoing: Lifecycle model, HR management
Start small, prove value, scale: — Pilot on one project
Measure improvements (schedule, cost, quality)
Refine processes
Roll out organization-wide
Automotive OEM approach (typical): — 3-year SE process transformation program
Target: ASPICE Level 3 (established, defined processes)
Investment: 2-3% of engineering headcount for process group
ROI: 10-20% reduction in rework, 15-30% reduction in defect rates
Follow these practices, and your projects will succeed.
PPT Content:
BEST PRACTICES: MANAGEMENT & ENABLING PROCESSES TECHNICAL MANAGEMENT: Planning & Control: ✓ WBS to 4-6 levels, integration milestones ✓ EVM tracking, 15-20% margin Decision: ✓ Gate criteria in advance ✓ Decision frameworks, CCB, impact analysis Measurement: ✓ 5-10 TPMs, automated, trend analysis Config & Info: ✓ Baselines at gates ✓ Single source of truth, version control Risk & Quality: ✓ Trigger-based mitigation ✓ Independent QA, gate authority ENABLING: Knowledge: ✓ Capture lessons end-of-phase ✓ Searchable, mandatory review Portfolio: ✓ Strategic alignment, quarterly reviews Infrastructure: ✓ Standardize tools, 3-5yr roadmap Lifecycle: ✓ 3-5 models, tailoring, asset library HR: ✓ Competency, training, succession **Implement over 3 years, start small, scale**

## Slide 29: Session 15 Key Takeaways and Connection to Session 16
Let's lock in the key takeaways from Session 15:
Key Takeaway 1: Three Process Categories — Technical processes (WHAT and HOW of SE) - Sessions 1-14
Technical management processes (MANAGE execution) - Today Part 1
Organizational enabling processes (ENABLE all processes) - Today Part 2
All 21 processes required for success
Key Takeaway 2: Management Foundation — Planning (WBS, schedule) prevents late surprises
Control (EVM) makes problems visible early
Decision management (gates, frameworks) prevents churn
Configuration management (baselines, CCB) prevents chaos
Key Takeaway 3: Measurement is Critical — Can't control what you don't measure
5-10 TPMs: progress, performance, quality
Trend analysis predicts problems
EVM forecasts cost and schedule
Key Takeaway 4: Knowledge Management Often Missing — Expert dependency, knowledge silos, repeated mistakes
Capture, organize, share, apply knowledge
Lessons learned must be APPLIED, not just documented
Key Takeaway 5: Portfolio Management Resolves Conflicts — Strategic alignment first, then resources
Prioritize: Strategic > Operational > Exploratory
Quarterly reviews, kill failing projects
Key Takeaway 6: Infrastructure Enables Everything — Standardized tools prevent chaos
5-10% R&D budget for infrastructure
3-5 year roadmap, centralized support
Key Takeaway 7: Process Excellence ≥ Technical Excellence — ADAP: Same team, same tech, different processes = success
Most failures due to process gaps, not technical gaps
Implement all 21 processes over 3 years
CONNECTION TO SESSION 16: EMERGING TRENDS
What we've learned: ISO/IEC 15288 framework (established, proven)
What's next: How is SE evolving?
Session 16 Topics: — Model-Based Systems Engineering (MBSE) maturity
Digital twins and digital threads
AI/ML in systems engineering
Autonomous systems SE challenges
Agile and DevOps in SE
Cloud-based SE collaboration
Cybersecurity by design
Sustainability and green SE
The question: How do management and enabling processes ADAPT to these trends?
Example: — AI/ML in SE → How to manage AI model development? (New lifecycle model)
Digital twins → What infrastructure needed? (Cloud compute, simulation platforms)
Agile SE → How to do gates in Agile? (Sprint reviews as micro-gates)
Session 15 gives you the foundation. Session 16 shows you the future.
Final thought:
ISO/IEC 15288 is 20+ years old, but still relevant. Why?
Because: — Technical processes may change (Agile vs waterfall)
Technologies evolve (AI, digital twins)
But management and enabling processes remain constant: — Still need planning, control, decisions
Still need knowledge management, portfolio management
Still need infrastructure, quality assurance
The fundamentals of Session 15 will serve your entire career.
Next session: How to apply these fundamentals to emerging trends.
PPT Content:
SESSION 15 KEY TAKEAWAYS 1. Three Process Categories (21 Total) • Technical (8): WHAT/HOW • Mgmt (8): Control execution • Enabling (5): Foundation 2. Management Foundation • Planning, control, decision, config • Prevents late surprises, chaos 3. Measurement Critical • TPMs, EVM make problems visible 4. Knowledge Management Often Missing • Capture, share, APPLY lessons 5. Portfolio Resolves Conflicts • Strategic alignment → resource allocation 6. Infrastructure Enables Everything • Standardized tools, 3-5yr roadmap 7. Process Excellence ≥ Technical Excellence • ADAP success via better processes **Next: Session 16 - Emerging Trends in SE** Preview: • MBSE maturity, digital twins, AI/ML • Autonomous systems, Agile SE • Cloud collaboration, cybersecurity • Sustainability **How do management/enabling processes adapt to trends?** **Session 15 foundation serves your entire career**

## Slide 30: 📝 INSTRUCTOR NOTES
Additional Resources
Approach: Process-Focused/Management
This session shifts from technical to managerial perspective. The pedagogy emphasizes:
Process Integration: Show how management processes enable technical processes
Real Consequences: Use ADAP case to show management process failures
Practical Tools: EVM, WBS, decision frameworks, TPMs
Organizational Context: Enabling processes operate at org level
Complete Framework: All 21 ISO/IEC 15288 processes integrated
Challenge: Students often find management processes "boring" compared to technical. Counter by showing ADAP case - technical excellence failed without management processes.
Challenge 1: "Why do we need all this process overhead? Can't we just engineer?
Response: Use ADAP case. Same engineers, same technology. Only difference: processes. Result: Success vs failure. Processes are not overhead, they're enablers.
Challenge 2: "EVM seems complicated. Can't we just track % complete?
Response: Show EVM forecasting power. At Month 12, EVM predicted $1.6M overrun. % complete showed "on track." Which would you trust?
Challenge 3: "Knowledge management sounds nice but impractical.
Response: Calculate cost of repeated mistakes. ADAP repeated integration error: $800K. Capturing and applying one lesson would have saved that. ROI clear.
Challenge 4: "These enabling processes are not my job, they're management's job.
Response: True, but you'll be affected. Understanding portfolio management helps you understand why your project lost resources. Understanding infrastructure helps you advocate for better tools.
Critical timing considerations:
Part 1 (Technical Management) is dense (Slides 9-20). Budget full 30 minutes. Can't compress.
Part 2 (Enabling) is less familiar to students. Budget 20 minutes, use examples heavily.
ADAP case revisited (Slide 28) can generate discussion. Set 8-minute timer.
If running short on time:
Condensed: Combine Slides 14-16 (Measurement, Config, Info) into 10 min instead of 15 min
Skip: Slide 17 (Risk revisited) - covered in Session 9
If extra time:
Tool demonstration: Show actual DOORS, MS Project, EVM dashboard
Workshop: Give students a scenario, have them create WBS or decision matrix
Extended ADAP: More detailed root cause analysis
Slide 7: Poll - "How many have experienced a project like ADAP?" Show of hands.
Slide 12: Interactive - "You're at Gate 2. Architecture doesn't meet cost target. What decision?" Debate go/no-go.
Slide 14: Quick exercise - "For your project, what are top 3 TPMs you'd track?" Brainstorm.
Slide 23: Case - "You have 10 projects, 5 engineers. How allocate?" Small groups (5 min).
Slide 28: "What one process would have most helped ADAP?" Vote and discuss.
Before class:
[ ] Prepare sample WBS (ADAS project, 4 levels)
[ ] Create EVM chart with sample data
[ ] Load decision matrix template
[ ] Prepare TPM dashboard example
[ ] Sample lessons learned from automotive project
Optional materials:
Real project plan (redacted) showing WBS, schedule
EVM tool demo (MS Project or equivalent)
ISO/IEC 15288 standard excerpt (processes)
Formative Assessment (During Session):
Quick check after Slide 11: "Calculate SPI and CPI for this scenario" (give numbers)
Quick check after Slide 15: "What baseline type at Month 18?" (Design baseline)
Quick check after Slide 23: "Categorize these 5 projects: Strategic, Operational, or Exploratory?
Summative Assessment (Future):
No specific exercise for Session 15
Will be assessed in final exam
Case study analysis (provide scenario, identify process gaps)
Students successfully understand Session 15 if they can:
List all 21 ISO/IEC 15288 processes in three categories
Explain how management processes enable technical processes
Apply WBS, EVM, decision frameworks to project scenarios
Define TPMs for a given system
Describe CCB process and baseline types
Explain knowledge management cycle and benefits
Apply portfolio prioritization to resource allocation scenarios
Backward Links:
Session 2: ISO/IEC 15288 introduced, today completes framework
Session 9: Project and risk management expanded today
Session 10: Decision and quality management deepened today
Session 13: LCC/TCO connects to portfolio management (project valuation)
Forward Links:
Session 16: Emerging trends require adapted management processes (Agile gates, AI model management, digital twin infrastructure)
Standards:
ISO/IEC/IEEE 15288:2023 (Full standard, all 21 processes)
ISO 21500:2021 (Project management guidance)
PMBOK Guide 7th Edition (Project management body of knowledge)
Automotive SPICE v3.1 (Process assessment model)
Books:
"Systems Engineering Management" by Benjamin Blanchard
"Earned Value Management" by Quentin Fleming
"The Knowledge-Creating Company" by Nonaka & Takeuchi
Tools:
MS Project, Primavera (planning, EVM)
JIRA, Azure DevOps (Agile project management)
Confluence, SharePoint (knowledge management)

## Slide 31: END OF SESSION 15 FRAMEWORK
Prepared for: Automotive Systems Engineering (AE ZG517 / AEL ZG517)
Session: 15 of 16
Status: Ready for PPT Development
Estimated PPT Slides: 28-30
Total Instructor Preparation Time: 3-4 hours